## Sheet1
BROLIX New Api List
| Task | Resource | Expanded Hours | Standard Hours | Start date | End date | Status
Card section:
| Show upgrade and luck card details api |  |  | 1 | 2017-05-19 | 2017-05-19
| Edit and remove cards api |  |  | 1 | 2017-05-19 | 2017-05-19
User section:
| Manage blocked pages in list Api |  |  | 2 | 2017-05-19 | 2017-05-19
| Show all blocked pages in remove list Api |  |  | 1 | 2017-05-19 | 2017-05-19
Ad section:
| Manage ads in ads list according to min, max and less number of viewer |  |  | 4 | 2017-05-19 | 2017-05-22
Winner section:
| By filling the number of winners then the number of coupons should be filled the same automatically Api |  |  | 4 | 2017-05-22 | 2017-05-22
Payment section:
| Manage payment Api |  |  | 8 | 2017-05-22 | 2017-05-23
| Upload mp3 file api. |  |  | 3 | 2017-05-23 | 2017-05-23
| Show uploaded file name and url api |  |  | 1 | 2017-05-24 | 2017-05-24