## Sheet1
Slides | Page Name | Errors | Status
Slide 1 | Users Section | -The live users is the number of the users who are using the App right now. Why it’s same with total users? | Done
Total winners should be the sum of cash winners & coupons winners. Why it’s 0?
|  | The “dashboard Filter” still not working. | Done
|  | I tried to block a user then the blocked user can use the app normally while he’s already blocked, so the block function should work directly and take him out of the App direct after blocking him, the current settings are waiting the blocked user to logout and block him when he try to login again, that’s not correct. | Backend Issue
|  | send message located on the boxes & above the table are not working. | Backend Issue
|  | send coupon located on the boxes & above the table are not working. | Backend Issue
|  | The number of pages in the table is not correct comparing with the data which appear by clicking on that number. For example, if the number under pages is 3 so by clicking on that number the pop up will show up only 1 page. | Done
| Add & Remove Admins issues | when I add someone as an admin to my page thru the App then he is listed in business users and that is correct, but when I click on show located on business users then the user is listed with 0 pages , and that is not correct, the number of his pages should be 1 which is the page that he has been added on it as an admin.Working | Done
|  | if I added someone as an admin thru “Add page” then the number of business users (users section) is not increased also the number of personal users (users section) is not decreased !! & if you fixed the previous issues, then by click on show located on business users then the pages number should also be increased. | Done
|  | if I added someone as an admin thru “edit page” then the number of admins in that page (pages section) is not increased and the number of business users is not increased also the number of personal users is not decreased !! & if you fixed the previous issues, then by click on show located on business users then the pages number should also be increased. | Done
Slide 2 | Add & Remove Admins Correct Procedures | remove him from personal users | Done
|  | add him to business users | Done
|  | the number of pages located in the table (users section) should be increased 1 page and navigate to the page details | Done
|  | the number of “Admins” for the page (that the user has been added on it) located in the table (pages section) should be increased and navigate to the user details. | Done
|  | the page should be listed in “My Pages” for that user.Working | Done
the user should appear in “current Admins” in the App with option “Remove”
|  | the number of pages located in the table (users section) should be increased 1 page and navigate to the page details. | Done
|  | the number of “Admins” for the page (that the user has been added on it) located in the table (pages section) should be increased and navigate to the user details | Done
Slide 3 | remove admin thru (App, Edit Page, Add page) | the number of pages located in the table (users section) should be decreased 1 | Done
|  | the number of “Admins” for the page (that the user has been added on it) located in the table (pages section) should be decreased | Done
|  | the page should be removed from “My Pages” for that user. | Done
|  | the user should removed from “current Admins” for that pag | Done
| Send Coupon | the description is not clear!!! Please resize the “send” bar & icon | Done
|  | the date format should be same like the App “Valid Thru: x Days” | Done
|  | if I use this function thru boxes (send to multi) & thru table (send to single) both of them showing the same title “Send Coupons to All Users” | Done
Slide 4 |  | the price is not clear!!! Please resize the “send” bar & icon | Done
|  | please use the Brolix sing instead of “B” | Pending
|  | if I use this function thru boxes (send to multi) & thru table (send to single) both of them showing the same title “Send Card to All Users” | Done
Slide 5 | Edit Profile | by changing the email or phone number the system should check for the duplication, I have change the phone & email to existed & registered phone & email and the system accepted them with no duplication error, and by searching on that email or phone the system show up two users hold the same data. Please fix it. | Done
| Add User | By adding new user everything is working well, but I am getting an error when i select the gender as “Female”, the system create the user normally but showing message “ please select one of these options, with highlighting the male option” | Done
Slide 6 | Pages Section | Send message located on “total pages & unpublished pages” & the send above the table should be sent directly to the “Page Inbox” located in “MY Pages/Inbox/inbox with notification, this function is not working. | Done
|  | The number of winners for each page in the table is not same with the number of winners in the App. | Backend Issue
|  | by clicking on the number of the Ads in the table the pop up contains a search, that search is not working, I think it should be search by date like the App. | Done
|  | please change the box color for “remove page request” because it’s same with other box in the same page. | Done
|  | -by clicking on “Admins” in the table the search in the pop up is not working , I think it’s search by name | Done
|  | The “dashboard Filter” still not working. | Done
| Add New Page & Edit Existed page | The “social media” & “add admin” are an optional | Pending
|  | please make the list of social media same with the list in the App | Pending
|  | please add back button during creating or editing the page and the data should be saved if I go back to the previous page. | Done
|  | What about adjusting the images?! | Done
|  | When you edit or create a new page then the cover picture become profile picture and the profile picture become cover picture!!! | Done
|  | The name on the coupons located inside my profile/gifts and the coupons located on the gifts inside all users profiles | Done
Slide 7 | Block & remove Page | The coupons that hold the name of the removed or blocked page located inside my profile/gifts and the coupons located on the gifts inside all users profiles should be disappeared | Backend Issue
|  | The blocked page or removed page should be disappeared from “My Pages” & “Pages” tab in home page. | Done
|  | The blocked page or removed page should be disappeared from “Favorite pages” | Done
|  | The winners for the removed or blocked page located everywhere in the app should be disappeared. | Pending
|  | The coupons in the store & favorite coupons which hold the page name for the blocked or removed page should be disappeared. | Pending
|  | The Ads that hold the page name for the removed or blocked page in home page/gifts, inside pages, my pages/Ads should be disappeared. | Done
| The difference between Block & Remove page: | The numbers of “Ads” & “Admins” in the table are not correct comparing with the data which appear by clicking on that number. For example, if the number under “Ads” or “Admins” is 3 so by clicking on that number the pop up will show up only 1 Ad or Admin. | Done
Slide 8 | Gifts Section | By clicking on show located on “Sent Cash” the amount in the table is not correct. | Backend Issue
|  | Contact winners function is not working. | Done
|  | Dashboard filter is not working. | Done
|  | By clicking on show located on “Cash Gifts”, the “cash status” in the table should always be “Delivered”, there is no pending status any more, if the user received his coupon then the status is Delivered. | Backend Issue
|  | By clicking on show located on any of the boxes, then clicking on “view” under coupon gift, the “coupon expiry date” should be same format like the App “X days”, and when reaching 0 Days that means the status will be “Expired”, if the user used the coupon then the expiry date should be 0 days (Exactly like the App). | Backend Issue
|  | By clicking on show located on “Hidden Gifts” then under the “Coupon Gifts” if you click on “View” then the code appear there is not correct. | Backend Issue
|  | By clicking on show located on “hidden gifts” you will see under coupon status “Active” and it should be “Valid” | Pending
| Cards Section | The “Total Sold Cards” should be the sum of “Used & Unused Cards”, the current values: the sum of used cards & unused cards does not equal the total sold cards!! | Backend Issue
|  | Please change the owner name in the table to “Buyer Name” | Done
|  | By clicking on “View” under “Used Ad” a lot of the data is not correct!! | Backend Issue
|  | The number of pages in the table is not correct comparing with the data which appear by clicking on that number. For example, if the number under pages is 3 so by clicking on that number the pop up will show up only 1 page. | Done
|  | Contact Buyers function is not working | Done
Slide 9 |  | Dashboard filter is not working. | Done
|  | Please change the text in the search from “Search by owner name” to “Search By Buyer Name” | Done
|  | By creating a new card and upload new picture please add the shadow on the new picture like all the images in the app, because the text on the card is not clear | Designing Issues
|  | the positions in the store should be based on the number of viewers or chances (the cards which hold the biggest numbers in the bottom and the lesser numbers in the top) | Done